## Sheet0
Feature ID | Functional Area (Integration ID) | Project ID and Name | Milestone | Assigned To | Role | State | Tower | Planned Start Date | Due Date | Application | Testing Signoff Status | Phase | WorkPacket | Task Name | Actual Start Date | Actual End Date | % Complete | Task Status | Comments
N+1 Testing |  | I402-S41809 S41809 |  | Balaji Rao | SAP FICO |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2019-09-24 | 2020-02-20 |  |  |  |  | Test Execution | 2019-09-24 |  | 60 | In Progress | Test cases for S4 1809 upgrade in N+1 FQ2 system.
1809 |  | P020-04 BPC-Planning |  | Balaji Rao | SAP FICO |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2019-12-06 | 2020-03-20 |  |  |  |  | Test Execution | 2019-12-12 |  | 50 | Hold | BPC planning security roles and Regression test scripts testing.
F7129-Tracking Approval |  | P196 GRDR |  | Balaji Rao | SAP FICO |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2020-06-02 | 2020-08-10 |  |  |  |  | Test case Design/Test Execution | 2020-05-22 |  | 30 | In Progress | GRDR -RSL payment tracking approval issues,dependency on Broker report it is under development.
7165-Outgoing Payment run trigger isssue |  | P196 GRDR |  | Balaji Rao | SAP FICO |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2020-03-16 | 2020-04-26 |  |  |  |  | Test case Design/Test Execution | 2020-03-11 | 2020-04-20 | 100 | Completed | GRDR -RSL Outgoing Payment run trigger isssue , two scenarios completed and shared for review.
7358-Outgoing Payment run trigger isssue and upload corrections |  | P196 GRDR |  | Balaji Rao | SAP FICO |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2020-03-16 | 2020-04-26 |  |  |  |  | Test case Design/Test Execution | 2020-03-11 | 2020-04-20 | 100 | Completed | GRDR -RSL Outgoing Payment run trigger isssue and upload corrections, three scenarios completed and shared for review.
F7888-Accounting Rule changes |  | P196 GRDR |  | Balaji Rao | SAP FICO |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2020-04-03 | 2020-04-13 |  |  |  |  | Test Execution | 2020-04-03 | 2020-04-13 | 100 | Completed | Regression scenarion related RSL tesing .
F7888-Accounting Rule changes |  | P196 GRDR |  | Balaji Rao | SAP FICO |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2020-04-09 | 2020-05-14 |  |  |  |  | Test Execution | 2020-04-03 | 2020-04-20 | 100 | Completed | Regression scenarion related RSL-re tesing, beacouse of busineee made some more changes initiated in accounting rules .
F7355-Separate accouting reports |  | P020 GL |  | Balaji Rao | SAP FICO |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2020-06-02 | 2020-08-10 |  |  |  |  | Test case Design/Test Execution | 2020-06-02 |  | 10 | In Progress | Execcuted dry run reports went it to database errors, waiting for changes.
F6162-Copy Function STAT to GAAP |  | P020-04 BPC-Planning |  | Balaji Rao | SAP FICO |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2020-04-15 | 2020-05-14 |  |  |  |  | Test case Design/Test Execution | 2020-04-15 | 2020-04-20 | 100 | Completed | Test cases created and gave KT to automation team and working on it.
F7992-EIP control report |  | P020 WEBI |  | Balaji Rao | SAP FICO |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2020-07-03 | 2020-08-28 |  |  |  |  | Test case Design/Test Execution | 2020-07-03 |  | 10 | In Progress | EIP control webi report testing.
F6013-RSL specific HANA review |  | P196 GRDR |  | Balaji Rao | SAP FICO |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2020-07-03 | 2020-08-28 |  |  |  |  | Test case Design/Test Execution | 2020-07-03 |  | 5 | In Progress | GRDR -RSL specific HANA review testing.
F6013-RSL Reporting off new resinsurance view |  | P196 GRDR |  | Balaji Rao | SAP FICO |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2020-07-03 | 2020-08-28 |  |  |  |  | Test case Design/Test Execution | 2020-07-03 |  | 5 | In Progress | GRDR -RSL Reporting off new resinsurance view testing.
F6099-Deletion of unused forms and Queries |  | P020-04 BPC-Planning |  | Balaji Rao | SAP FICO |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2020-07-10 | 2020-09-10 |  |  |  |  | Test case Design/Test Execution | 2020-07-10 |  | 5 | In Progress | BPC planning security roles delection of unsed forms and queries.
F7992-EPIP Compasation control report |  | P020 WEBI |  | Balaji Rao | SAP FICO |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2020-07-16 | 2020-09-10 |  |  |  |  | Test case Design/Test Execution | 2020-07-16 |  | 5 | In Progress | EPIP bo the detail report and summary report testing.
N/A |  | P158 Online Servicing |  | Bilasini Sabut | Test Specialist |  | /Distribution, Marketing & Communications/Brand & Marketing | 2019-12-20 | 2020-07-29 |  |  |  |  | SIT testing | 2019-12-20 |  | 80 | In Progress | Test execution blocked/impacted due to defects and data issues.
I91 |  | I91_IP013-005 DXC BPO/TPA - Lift and Shift of VARI |  | Harshitha T V | Test Analyst |  | /Client Solutions/Administer Policy | 2019-12-16 | 2020-10-30 |  |  |  |  | Test Design | 2019-12-16 |  | 53 | In Progress | Test Scripting is in progress
I207, I41, I214, I89 |  | P013-002 wmA Upgrade |  | Jujjarapu Nandini | Test Analyst |  | /Client Solutions/New Business | 2020-07-12 | 2020-07-17 |  |  |  |  | Tracker efforts for Reged day2 Fast follow and 19.03 Validation | 2020-07-12 |  | 65 | In Progress | Validation is in progress
I207, I41, I214, I89 |  | P013-002 wmA Upgrade |  | Jujjarapu Nandini | Test Analyst |  | /Client Solutions/New Business | 2020-07-12 | 2020-07-16 |  |  |  |  | Working on Regression TC | 2020-07-12 | 2020-07-16 | 100 | In Progress | Regression TC for RegEd application
I207, I41, I214, I89 |  | P013-002 wmA Upgrade |  | Jujjarapu Nandini | Test Analyst |  | /Client Solutions/New Business | 2020-07-12 | 2020-07-17 |  |  |  |  | Com and Statement file validation for com accounting | 2020-07-12 |  | 50 | In Progress | Com and Statement file validation for com accounting
I207, I41, I214, I89 |  | P013-002 wmA Upgrade |  | Jujjarapu Nandini | Test Analyst |  | /Client Solutions/New Business | 2020-07-16 | 2020-07-17 |  |  |  |  | Data setup in RegEd | 2020-07-16 |  | 80 | completed | Preparing data setup sheet and key in in RegEd application
I207, I41, I214, I89 |  | P013-002 wmA Upgrade |  | Jujjarapu Nandini | Test Analyst |  | /Client Solutions/New Business | 2020-07-12 | 2020-07-14 |  |  |  |  | E2E TC design | 2020-07-12 | 2020-07-14 | 100 | completed | Working on E2E TC
I89 |  | P013-002 wmA Upgrade |  | Nandkishore Shukla | Test Analyst |  | /Client Solutions | 2020-01-13 | 2020-07-15 |  |  |  |  | wmA Upgrade - Interfaces - Correspondence and Axway validation | 2020-01-13 |  | 98 | In progress | Cat 2 test cases pending for execution as part of wmA Interfaces
I89 |  | P013-002 wmA Upgrade |  | Nandkishore Shukla | Test Analyst |  | /Client Solutions | 2020-02-11 | 2020-07-15 |  |  |  |  | wmA Upgrade - Interfaces - New-Firm Testing Validation | 2020-02-11 |  | 80 | In progress | Blocked
I89 |  | P013-002 wmA Upgrade |  | Nandkishore Shukla | Test Analyst |  | /Client Solutions | 2020-07-03 | 2020-09-03 |  |  |  |  | wmA Upgrade - Interfaces - Misdirected mail | 2020-07-03 |  | 90 | In progress | Execution In Progress
NA |  | Quarterly Closure |  | Narendranath Reddy | Automation Tester |  | Quarterly Closure | 2020-05-15 | 2020-07-06 |  |  |  |  | Test Automation Design | 2020-05-15 | 2020-07-06 | 100 | Completed | E2E Quatterly closer phase Completed.
NA |  | TDM Flow |  | Narendranath Reddy | Automation Tester |  | TDM | 2020-07-13 | 2020-07-20 |  |  |  |  | Test Automation Design | 2020-07-13 |  | 40 | Inprogess | Working on TDM Flow 2 test cases
|  | CTD |  | Narendranath Reddy | Automation Tester |  | CTD | 2020-07-15 | 2020-07-20 |  |  |  |  | Test Automation Design | 2020-07-15 |  | 20 | Inprogess | Creating CTD Model for Firelight.
NA |  | NA SAP ETE |  | Niveditha | Automation Tester |  | /Corporate Solutions/SAP ETE | 2020-06-30 | 08-30-2020 |  |  |  |  | Test case Automation | 2020-06-30 |  | 35 | In Progress | Working on SAP ETE(Vendor Upload->Vendor Approval->Invoice Creation->Invoice Approval->Payment->Kyriba.(Blocked due to Kyriba URL is down due to maintainance)
DXC job - file upload |  | EDS EDS |  | Parmesh Krishna | Tester |  | EDS | 2020-05-26 | [5 empty] | Job executions | 2020-05-26 |  | 60 | In Progress
F8002,F8551 |  | EDS EDS |  | Parmesh Krishna | Tester |  | EDS | 06-15-2020 | 06-25-2020 |  |  |  |  | validation | 2020-06-15 | 2020-07-15 | 100 | Completed
F5064,F5065 |  | EDS EDS |  | Parmesh Krishna | Tester |  | EDS | 2020-07-01 | 07-17-2020 |  |  |  |  | Validation | 2020-07-01 |  | 60 | In Progress
F9042 |  | EDS EDS |  | Parmesh Krishna | Tester |  | EDS | 07-13-2020 | [5 empty] | Test Case Design | 2020-07-13 | 2020-07-13 | 100 | Completed
F8386 |  | EDS EDS |  | Parmesh Krishna | Tester |  | EDS | 07-13-2020 | 07-17-2020 |  |  |  |  | Test Case Design | 2020-07-13 | 2020-07-13 | 100 | In Progress
F3424 - Configuration Feature: Portray As (PM, Employee, and TPA Audiences),F3419 - Configuration Feature: Canned Reports,F3415-Configuration Feature: Policy/Contract Details,F3413-Configuration Feature: Book of Business |  | P158 Online Servicing |  | Phanikishan Palla | Senior System Engineer |  | /Distribution, Marketing & Communications/Brand & Marketing | 2020-06-28 | 2020-07-18 |  |  |  |  | Test Case Design/Modification and Execution (ST/ SIT) Sprint 29 |  |  | 50 | In Progress
N/A |  | P158 Online Servicing |  | Phanikishan Palla | Senior System Engineer |  | /Distribution, Marketing & Communications/Brand & Marketing | 2020-03-16 | [5 empty] | OLS SIT-SEDS/TEDS Agents and Customers registration and activation. |  |  |  | In Progress
N/A |  | P158 Online Servicing |  | Phanikishan Palla | Senior System Engineer |  | /Distribution, Marketing & Communications/Brand & Marketing | 2020-03-16 | [5 empty] | OLS SIT-OLSQA Firms and Agents association for the registered agents. |  |  |  | In Progress
N/A |  | P158 Online Servicing |  | Phanikishan Palla | Senior System Engineer |  | /Distribution, Marketing & Communications/Brand & Marketing | 2020-03-16 | [5 empty] | Creating BOA users in AEM to access in OLS. |  |  |  | In Progress
N/A |  | P158 Online Servicing |  | Phanikishan Palla | Senior System Engineer |  | /Distribution, Marketing & Communications/Brand & Marketing | 2020-07-14 | 2020-07-15 |  |  |  |  | Adding the STG agents in to OLSQA | 2020-07-14 | 2020-07-15 | 100 | Completed
NA |  | OTH OTHER |  | Priyotosh Ganguly | Tools Administrator |  | Other | 2019-07-13 | 2020-07-17 |  |  |  |  | Admin Activities | 2019-07-13 | 2020-07-17 | 100 | Completed | Service Now Ticket maintenance
NA |  | OTH OTHER |  | Priyotosh Ganguly | Tools Administrator |  | Other | 2019-07-13 | 2020-07-17 |  |  |  |  | Admin Activities | 2019-07-13 | 2020-07-17 | 100 | Completed | Micro Focus ticket Management
NA |  | OTH OTHER |  | Priyotosh Ganguly | Tools Administrator |  | Other | 2019-07-13 | 2020-07-17 |  |  |  |  | Admin Activities | 2019-07-13 | 2020-07-17 | 100 | Completed | Worksoft Certify ticket maintenance
NA |  | OTH OTHER |  | Priyotosh Ganguly | Tools Administrator |  | Other | 2019-07-13 | 2020-07-17 |  |  |  |  | Admin Activities | 2019-07-13 | 2020-07-17 | 100 | Completed | ALM User access and maintenance
NA |  | OTH OTHER |  | Priyotosh Ganguly | Tools Administrator |  | Other | 2019-07-13 | 2020-07-17 |  |  |  |  | Admin Activities | 2019-07-13 | 2020-07-17 | 100 | Completed | Sync of Initiative
NA |  | OTH OTHER |  | Priyotosh Ganguly | Tools Administrator |  | Other | 2019-07-13 | 2020-07-17 |  |  |  |  | Admin Activities | 2019-07-13 | 2020-07-17 | 100 | Completed | Non-Conformance of Brighthouse ALM
NA |  | OTH OTHER |  | Priyotosh Ganguly | Tools Administrator |  | Other | 2019-07-13 | 2020-07-17 |  |  |  |  | Admin Activities | 2019-07-13 | 2020-07-17 | 100 | Completed | Daily Report generation for Non-compliance
NA |  | OTH OTHER |  | Priyotosh Ganguly | Tools Administrator |  | Other | 2019-07-13 | 2020-07-17 |  |  |  |  | Admin Activities | 2019-08-26 | 2020-07-17 | 100 | In Progress | Follow up and co-ordination with the team to make ALM compliant
NA |  | OTH OTHER |  | Priyotosh Ganguly | Tools Administrator |  | Other | 2019-07-13 | 2020-07-17 |  |  |  |  | Admin Activities | 2019-07-13 | 2020-07-17 | 100 | Completed | Feature Sync with Rally
|  |  |  | Vaibhav | Team Member |  | Actuarial | [6 empty] | QA Design |  |  |  |  | Assisting "Actuarial" team for design off Automation and Automated SQL querries scripts. E2E analysis.
F7244 |  | WMA17 |  | Chandra Gangireddy | SAP FSCD |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2020-07-13 | 2020-07-17 |  |  |  |  | Test Execution | 2020-07-13 | 2020-07-13 | 100 | In Progress
F8727 |  |  |  | Chandra Gangireddy | SAP FSCD |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2020-07-16 | 2020-07-16 |  |  |  |  | Test Execution | 2020-07-16 | 2020-07-16 | 100 | Completed
F3707 |  | WMA17 |  | Chandra Gangireddy | SAP FSCD |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2020-07-13 | 2020-07-17 |  |  |  |  | Test Execution | 2020-07-13 | 2020-07-17 | 100 | In Progress
F1926 |  | WMA17 |  | Chandra Gangireddy | SAP FSCD |  | /Corporate Solutions/Finance, Risk & Accounting/Accounting & Reporting | 2020-07-13 | 2020-07-17 |  |  |  |  | Test Execution | 2020-07-13 | 2020-07-17 | 100 | In Progress
Webi-SAP Hana view Validation |  | Illustrations Illustrations |  | Prathibha BN | Automation Lead |  | Brighthouse/In flight projects | 2020-06-29 | 2020-07-06 |  |  |  |  | Test Case Design | 2020-06-29 | 2020-07-13 | 100 | Complete | Automation of Webi-SAP Hana view Validation for Monthly is complete.
SAP s4 User Password Reset |  | SAP GL SAP GL |  | Prathibha BN | Automation Lead |  | Brighthouse/In flight projects | 2020-07-03 | 2020-07-10 |  |  |  |  | Test Case Design | 2020-07-03 | 2020-07-13 | 100 | Complete | Automation of SAP s4 User Password Reset for background locked users is complete.
SAP s4 User Password Reset |  | SAP GL SAP GL |  | Prathibha BN | Automation Lead |  | Brighthouse/In flight projects | 2020-07-14 | 2020-07-22 |  |  |  |  | Test Case Design | 2020-07-14 |  | 20 | In Progress | Enhancements for SAP s4 User Password Reset for background locked users is in progress.
Webi-SAP Hana view Validation |  | Illustrations Illustrations |  | Prathibha BN | Automation Lead |  | Brighthouse/In flight projects | 2020-07-14 | 2020-07-22 |  |  |  |  | Test Case Design | 2020-07-14 |  | 70 | In Progress | Automation of Webi-SAP Hana view Validation for Quarterly and Yearly is in progress.
Control Check Validation |  | Acturials Acturials |  | Prathibha BN | Automation Lead |  | Brighthouse/In flight projects | 2020-07-14 | 2020-07-22 |  |  |  |  | Test Case Design | 2020-07-14 |  | 70 | In Progress | Automation of Control check validation for DCS to EDIP is in progress.
F1915 - EDS (PPLUS) - SAP BOE (SOURCE) -Compensation Reporting |  | I207 P013-011-02-01 - DXC BPO/TPA - Compensation - wmA10 upgrade |  | Rashmi Choudhary | Sr. Test Analyst |  | Client Solutions | 2019-01-01 | 2020-06-26 |  |  |  |  | Planning, Design, Execution | 2019-01-01 |  | 60 | In Progress | Test execution in progress
|  | I214 P013-012 - DXC BPO/TPA - Licensing and Appointments |  | Rashmi Choudhary | Sr. Test Analyst |  | Client Solutions | 2020-07-10 | 2020-07-31 |  |  |  |  | Planning, Design, Execution | 2020-07-10 |  | 80 | In Progress | Test case design in progress
Compensation Data Load in EIQ and EQ4 |  | EDS/OLX/DXC Enterprise Data Store |  | Nitish Kumar | Sr. Test Analyst |  | EDS | [6 empty] | Data Load in EIQ and EQ4 |  |  |  | In Progress | This is a continuous daily task
F1904 Test Case execution |  | EDS/OLX/DXC Enterprise Data Store |  | Nitish Kumar | Sr. Test Analyst |  | EDS | 2020-03-23 | 2020-05-29 |  |  |  |  | Test Case execution | 2020-03-23 | 2020-05-29 | 100 | In Progress | Sanyo confirmed that it will be taken care after it will be done after upcoming release.
F9057 Test Case writing |  | EDS/OLX/DXC Enterprise Data Store |  | Nitish Kumar | Sr. Test Analyst |  | EDS | 2020-07-07 | 2020-07-17 |  |  |  |  | Test Case writing | 2020-07-07 | 2020-07-17 | 100 | Completed
F9042 Test Case writing |  | EDS/OLX/DXC Enterprise Data Store |  | Nitish Kumar | Sr. Test Analyst |  | EDS | 2020-07-14 | 2020-07-17 |  |  |  |  | Test Case writing | 2020-07-14 | 2020-07-17 | 100 | Completed
F9093 Test Case writing |  | EDS/OLX/DXC Enterprise Data Store |  | Nitish Kumar | Sr. Test Analyst |  | EDS | 2020-07-14 | 2020-07-17 |  |  |  |  | Test Case writing | 2020-07-14 | 2020-07-17 | 100 | Completed
NA |  | Others Converting Manual TC To VAPI-XP |  | Sakuntala Tripathy | Automation Tester |  | Others | 2020-06-12 | 2020-06-30 |  |  |  |  | Test Case Design - Automation | 2020-06-12 | 2020-06-30 | 100 | In Progress | Converting Manual test case into Automation VAPI-XP test case
NA |  | Others Prearring automation script of BOBJ reporting |  | Sakuntala Tripathy | Automation Tester |  | Others | 2020-06-12 | 2020-06-22 |  |  |  |  | Test Case Design - Automation | 2020-07-08 | 2020-07-22 | 100 | In Progress | Showed demo to functional team.Working on enhancements.
F1943 |  | I89 WMA Upgare |  | ssubramaniyam | QMO Team member |  | /Client Solutions/WmA upgrade | 2020-01-22 | 2020-04-10 |  |  |  |  | wmA Upgrade - Interfaces - File Validation (After code refreshed from DXC) | 2019-01-22 | 2020-04-10 | 100 | In Progress | Currently working for 07_15 DXC cycle.
F5331 |  | I89 WMA Upgare |  | ssubramaniyam | QMO Team member |  | /Client Solutions/WmA upgrade | 2020-03-12 | 2020-03-16 |  |  |  |  | wmA Upgrade - Interfaces - Post Issue Validation | 2020-03-12 | 2020-04-10 | 100 | In Progress | Validating Misdirected files
F5331 |  | i89 WMA Upgare |  | ssubramaniyam | QMO Team member |  | /Client Solutions/WmA upgrade | 2020-03-17 | 2020-03-27 |  |  |  |  | wmA Upgrade - Interfaces - Axway validation | 2020-03-17 | 2020-04-10 | 100 | In Progress | Writing TC's for Misdirected Mail
F2526 |  | i89 WMA Upgare |  | ssubramaniyam | QMO Team member |  | /Client Solutions/WmA upgrade | 2020-03-01 | 2020-04-05 |  |  |  |  | wmA Upgrade - Interfaces - EDIP - Axway - Shared dr | 2020-03-01 | 2020-04-10 | 100 | In Progress | Working on E2E TC design
F1550 |  | i89 WMA Upgare |  | ssubramaniyam | QMO Team member |  | /Client Solutions/Correspondence/Daily Transaction Confirms | 2020-03-01 | 2020-04-10 |  |  |  |  | wmA Upgrade - Interfaces - Correspondence Execution | 2020-03-01 | 2020-04-10 | 100 | In Progress | Working on E2E execution for 07_16 cycle
I91 |  | I91_IP013-005 DXC BPO/TPA - Lift and Shift of VARI |  | Umesh Yalavarthi | Test Analyst |  | /Client Solutions/Administer Policy | 2019-12-16 | 2020-10-30 |  |  |  |  | Test Design | 2019-12-16 |  | 53 | In Progress | Test Scripting is in progress
I92 |  | I92_P013-006 P013-006 - DXC BPO/TPA - VRPS Conversion |  | Umesh Yalavarthi | Test Analyst |  | /Client Solutions/Administer Policy | 2020-03-16 | 2020-10-30 |  |  |  |  | Test Design | 2020-03-16 |  | 12 | In Progress | Test Scripting is in progress
I31 |  | I31 P211 - Enterprise Death Match and Lost Policy Holders |  | Umesh Yalavarthi | Test Analyst |  | /Client Solutions/Administer Policy | 2020-04-15 | 2020-10-30 |  |  |  |  | Test Execution | 2020-04-15 |  | 30 | In Progress | Test Execution is in progress
I255 |  | I255_P106-03 P106-03 - Non-Core Policy Admin - RIS |  | Umesh Yalavarthi | Test Analyst |  | /Client Solutions/Administer Policy | 2020-04-20 | 2020-10-30 |  |  |  |  | Test Design | 2020-04-20 |  | 14 | In Progress | Test Scripting in progress
I255 |  | I255_P106-03 P106-03 - Non-Core Policy Admin - RIS |  | Umesh Yalavarthi | Test Analyst |  | /Client Solutions/Administer Policy | 2020-05-18 | 2020-10-30 |  |  |  |  | Test Design | 2020-05-18 |  | 5 | In Progress | Test Excution is in progress
REQ9607 Metlife Customer preferences |  | AEM I47 - P225 - Marketing XD & Incremental Web Design |  | Vidya Chinnaswamy | Sr. Test Analyst |  | IT & data/ IT Security | 2020-04-15 | 07-30-20 |  |  |  |  | Test data creation | 2020-04-15 |  | 95 | In Progress | Metlife preferences test cases writing and execution
F1335. F8450 |  | AEM I47 - P225 - Marketing XD & Incremental Web Design |  | Vidya Chinnaswamy | Sr. Test Analyst |  | IT & data/ IT Security | 2020-04-15 | 07-30-20 |  |  |  |  | Test data creation | 2020-04-15 |  | 95 | In Progress | Agent and Firm Preferences, BHF Customer Preferences and Metlife Customer Preferences UAT evidences preparation for Demo
F3781 |  | Initiative I48: SuccessFactors - Ongoing Maint./Enhancements | MI256: September Release 09/24 - 09/26 | Bharath Murthy |  | Requirements | Human Resources | 07-06-2020 | 09-30-2020 | SuccessFactors | FALSE
F4863 |  | Initiative I27: P201 - Structured Reinsurance |  |  |  | Backlog | Accounting & Reporting | 07-07-2020 | 09-24-2020 | WEBI | FALSE
F7370 |  | Initiative I490: Telephony - Ongoing Maint./ Enhancement |  | Anand Raghavendran;Biju Nair |  | UAT In Progress | Telephony | 07-09-2020 | 07-31-2020 | Five9 | FALSE
F8990 |  | Initiative I48: SuccessFactors - Ongoing Maint./Enhancements |  | Bharath Murthy |  | Requirements | Human Resources | 07-06-2020 | 09-30-2020 | SuccessFactors | FALSE
F9049 |  | Initiative I223: P222 - Salesforce - Ongoing Maint./Enhancements | MI255: August 08/06 - 08/08 Frost Exceptions | Manohar Venkataraman |  | UAT Pending | Distribution & Marketing | 07-08-2020 | 08-07-2020 | Salesforce | FALSE
F9102 |  | Initiative I546: ServiceNow - Ongoing Enhancements/Maintenance |  |  |  | Design | IT Infrastructure | 07-06-2020 | 08-31-2020 | Infrastructure Delivery | FALSE
F9103 | [5 empty] | In Production | IT Infrastructure | 07-06-2020 | 07-31-2020 |  | FALSE
F9108 |  | Initiative I197: Credit Risk Platform - Ongoing Maint./Enhancements related to Market Conditions Variations | MI227: July 07/09 - 07/11 Freeze exceptions |  |  | Complete | Enterprise Risk | 07-06-2020 | 07-09-2020 | Credit Risk Platform | FALSE
F9112 | Inforce Administration |  | MI296: July 07/23 - 07/25 Frost Exceptions | Punam Sarkar |  | Pending Go Live (Ready for Release Mgmt.) | Client Solutions | 07-06-2020 | 07-09-2020 |  | TRUE
F9116 | Licensing & Appointments | Initiative I214: P013-012 - DXC BPO/TPA - Licensing and Appointments | MI191: 19.03 Release_Go Live_DAY1 (04/10 2020) | Punam Sarkar |  | Build/Config | *Portfolio Management | 07-07-2020 | 07-27-2020 | SAP CPI | FALSE
F9119 |  | Initiative I359: Aladdin - Ongoing Maint./Ehancements |  |  |  | Build/Config | Investment Management | 07-07-2020 | 08-31-2020 | Infrastructure Delivery | FALSE
F9125 |  | Initiative I550: BEAM Application Onboarding (Net New Apps) |  | Vinod Pawar |  | Requirements | *Portfolio Management | 07-07-2020 | 09-10-2020 |  | FALSE
F9126 |  | Initiative I551: BEAM - Ongoing Enhancement/Maintenance |  |  |  | Requirements | *Portfolio Management | 07-06-2020 | 08-27-2020 |  | FALSE
F9127 |  | Initiative I161: Kyriba - Ongoing Maint./Enhancements | MI296: July 07/23 - 07/25 Frost Exceptions |  |  | Requirements | Treasury | 07-08-2020 | 07-23-2020 | Redwood | FALSE
F9156 |  | Initiative I359: Aladdin - Ongoing Maint./Ehancements |  |  |  | Build/Config | Accounting & Reporting | 07-08-2020 | 07-31-2020 | SAP EIP | FALSE
F9157 |  | Initiative I179: BPC Consolidations - Ongoing Maint./Enhancements | MI201: August Release (08/20 - 08/22) |  |  | Design | Accounting & Reporting | 07-08-2020 | 08-20-2020 | BPC Consolidations | FALSE
F9162 |  |  | MI296: July 07/23 - 07/25 Frost Exceptions | Chandra Gangireddy;Manjunatha A Ramalingachar |  | Pending Go Live (Ready for Release Mgmt.) | Accounting & Reporting | 07-09-2020 | 07-23-2020 | SAP FSCD | FALSE
F9163 |  |  | MI296: July 07/23 - 07/25 Frost Exceptions |  |  | Build/Config | Accounting & Reporting | 07-09-2020 | 07-20-2020 | SAP FSCD | FALSE
F9166 | Licensing & Appointments | Initiative I214: P013-012 - DXC BPO/TPA - Licensing and Appointments | MI296: July 07/23 - 07/25 Frost Exceptions | Punam Sarkar |  | Pending Go Live (Ready for Release Mgmt.) | Client Solutions | 07-09-2020 | 07-17-2020 |  | TRUE
F9173 |  | Initiative I490: Telephony - Ongoing Maint./ Enhancement |  |  |  | Design | Telephony | 07-09-2020 | 08-31-2020 | Five9 | FALSE
F9174 |  | Initiative I490: Telephony - Ongoing Maint./ Enhancement |  |  |  | Design | Telephony | 07-09-2020 | 08-31-2020 | Five9 | FALSE
F9194 | [5 empty] | Requirements | *Portfolio Management | 07-06-2020 | 08-07-2020 |  | FALSE
F9203 | Registration | Initiative I89: P013-002 - DXC BPO/TPA - Track 4 wmA10 upgrade to wmA17 | MI191: 19.03 Release_Go Live_DAY1 (04/10 2020) | Punam Sarkar |  | Build/Config | *Portfolio Management | 07-07-2020 | 07-27-2020 | EDS | FALSE
F9205 | Licensing & Appointments | Initiative I214: P013-012 - DXC BPO/TPA - Licensing and Appointments | MI296: July 07/23 - 07/25 Frost Exceptions |  |  | Pending Go Live (Ready for Release Mgmt.) | Client Solutions | 07-06-2020 | 07-23-2020 |  | TRUE
F9221 |  | Initiative I490: Telephony - Ongoing Maint./ Enhancement |  |  |  | Complete | Telephony | 07-06-2020 | 07-16-2020 | Five9 | FALSE
F9237 | Treasury | Initiative I214: P013-012 - DXC BPO/TPA - Licensing and Appointments | MI191: 19.03 Release_Go Live_DAY1 (04/10 2020) | Punam Sarkar |  | Requirements | *Portfolio Management | 07-07-2020 | 07-27-2020 |  | FALSE
F9243 | Treasury | Initiative I214: P013-012 - DXC BPO/TPA - Licensing and Appointments | MI191: 19.03 Release_Go Live_DAY1 (04/10 2020) | Punam Sarkar |  | Requirements | *Portfolio Management | 07-07-2020 | 07-27-2020 |  | FALSE

## Sheet1
Continents |  | Requirements | Plan | Design | Exit
Requirements |  | AnalyseRequirements | DevelopTestStrategy | Develop Test Scenarios | Closure Report
Plan |  | TestEstimates | DevelopSystemIntegrationTestPlan | Develop Test Cases | Prepare Test Metrics
Design |  | Project Schedule |  | Traceability | Others
Exit |  |  |  | Test Data creation
Test Readyness Review
Execute Manual test Specifications
Regression Test
AnalyseRequirements | TestEstimates | Project Schedule | DevelopTestStrategy | DevelopSystemIntegrationTestPlan | Develop Test Scenarios | Develop Test Cases | Traceability | Test Data creation | Test Readyness Review | Execute Manual test Specifications | Regression Test | Closure Report | Prepare Test Metrics | Others
Analyse the scope of project | Create, Review, Rework and Baseline Test Estimates | Create, Review, Rework and Baseline Project Schedule | Create, Review, Rework and Baseline Master Test Strategy | Create, Review, Rework and Baseline Master Test Plan | Create, Review, Rework and Baseline Test scenarios. | Create, Review, Rework and Baseline Test Cases | Upload Features into ALM (Requirements Module) - Admin | Test Data Plan | Create, Review and Rework TRR score card | Create Test Sets in ALM (Test Lab module) | Run manual Regression tests | Create, Review, Rework and Baseline Test Summary Report | Collect Test Metrics | Document Lessons Learned
Walk through requirements (features) in CA Rally | Get Test Estimates signed-off from BHF (Tyler) / ITSO | Get Project Schedule approved by Program Manager | Get Master Test Strategy sign-off from ITSO / Program Manager | Get Master Test Plan sign-off from ITSO / Program Manager | Get Test Scenarios sign-off from ITSO / Program Manager | Get Test Scenarios sign-off from ITSO / Program Manager | Map test cases to features | Create or Order test data | Communicate TRR score to Development Team and Program Manager / ITSO | Pull the test cases into Test sets | Execute Automation test specifications | Get Test Summery Report Signed-off | Review Test Metrics | Document Actions & Improvement required
Walk through supportive documents (Architecture ….) |  | Get approval for last date for QMO TE Sign-off |  |  |  | Upload test cases into ALM (Test Plan) | Generate RTVM from ALM | SME/Peer Review or verify the created test data | Provide TRR sign-off if TRR score is above 85% | Create, Review, Retest Defects | Restest Defect Fixes |  | Actions to mitigate contractual liability | Actions to mitigate contractual liability
Create, Update R.A.I.D log in Rally | [6 empty] | Get RTVM approved by ITSO / Program Manager | Request recreate test data |  | Send Daily Test execution Report | Rework on test script wrt Defect Fixes
Send Daily Defects Report / Attend defects triage call